## Sheet1
Project: | ES Coursework
| Month | November |  |  |  | December
| Week Commencing | 7th-10th | 11-17th | 18th-24th | 25th-1st | 2nd-4th
Planning | [6 empty] | Ensure any bugs are documentation (roughly, can be marked up formally later)
GANTT Chart Creation
Designing & Testing | [6 empty] | Include testing macros
Kanban
Regression testing file
FSM
DS & documentation for ds
memory managenment eeprom flash memory, pointers etc
Programming
Synchronisation
Main Menu (viewing ppl) & movement between main menu
select interrupt screen
Serial ADD
Serial PST
Serial GRD
Serial SAL
Serial CJT
Serial DEL
OUTPUTs & ERRORS
UDCHARS
FREERAM
EEPROM
SCROLL
HCI
Documentation
Reflection
Final collation & Checks [Grammer, Comments, Structure & Rules -> View specification]
Pointer to current Week: |  | ^^^^^^^
Was Plan Successful (Y/N)